## Proforma -I
Annexure-1
Statement of showing the monthly progress of Original Works
Civil Works costing Rs. 2 Crore and above
Electrical works costing Rs. 30 lacs and above
Horticulture works consting Rs. 4 lacs and above
Sr. No. | Name of Work and location | Estimated Cost | Tendered Cost (Rs. in lacs) | % above below Schedule of Rates (SOR) | Agreement Number | Agency | Date of Start | Date of Completion | Physical Progress | Name of Engineer incharge with Official Address | Remarks
Circle Faridkot
WSS Faridkot
1 | Providing W/S Scheme Bajakhana Under Word Bank Assited Project | 277.45 | 233.28 | 15.92% | 2012-11-09 | M/s Mittal Construction Company Jaitu. | 2012-11-11 | 2013-09-30 | Work Complete | Executive Engineer W/S & Sanitation Division, Faridkot. | -
WSS Malout
Water Supply
1 | Denewala (NRWSP) | 2.17 | 139.17 | 4.22% | 669 | Sh. Sanjeev Kumar Choudhary Govt Contr. | 10.03.2014 | Work in Progres | Work in Progres | Sh. Parmod Chand Executive Engineer
2 | Bharu (NRWSP) | 2.29 | 149.7 | 10.6% | 670 | Sh. Pankaj Arora Govt Contr. | 10.03.2014 | Work in Progres | Work in Progres | Sh. Parmod Chand Executive Engineer
3 | Shamkot (NRWSP) | 2.69 | 260.82 | 9.8% | 627 | Sh. Ashok kumar Govt Contr. | 07.03.2013 | 06.12.2013 | 100% | Sh. Parmod Chand Executive Engineer
4 | Ghumiara (NRWSP) | 2.09 | 186.1 | 5.21% | 632 | Sh. Ashok kumar Govt Contr. | 16.04.2013 | 09.02.2014 | 100% | Sh. Parmod Chand Executive Engineer
Sewerage Scheme
1 | Middu Khera (Sewerage Scheme) | 6.33 | 518.26 | 17.84% | 90 | M/s Hardev Singh & Co. Mandi Goneana | 09.11.2013 | Work in Progres | Work in Progres | Sh. Parmod Chand Executive Engineer
2 | Beedowali (Sewerage Scheme) | 4.13 | 394.86 | 16.69% | 89 | M/s Hardev Singh & Co. Mandi Goneana | 09.11.2013 | Work in Progres | Work in Progres | Sh. Parmod Chand Executive Engineer
3 | Ghumiar Khera (Sewerage Scheme) | 2.09 | 207.76 | 10.84% | 77 | Sh. Ashok Kumar Govt Contr. | 13.05.2013 | 02.02.2014 | 100% | Sh. Parmod Chand Executive Engineer
4 | Daula (Sewerage Scheme) | 2.38 | 241.93 | 2.59% | 76 | M/s Hardev Singh & Co. Mandi Goneana | 02.05.2013 | 02.01.2014 | 100% | Sh. Parmod Chand Executive Engineer
WSS DIVN. NO.1 MUKTSAR
1 | Water Supply Scheme Bhalliana (Under NRDWP-SWAP Mode) | 237.18 | 242.07 | 2.06% above | 514/2013-14 | Mittal Contruction Company, jaito | 2014-03-03 | 2015-03-03 | 80% Completed | Sh. Yadwinder Singh Dhillion,Executive Engineer, Water supply and Sanitation Division No.1 Shri Muktsar Sahib. | work in progress
2 | Sewarge Scheme Bhangchari (Under World Bank Project) | 605.61 | 540.29 | 10.79% below | PRWSS-W---DIV- 48 | Ashok Kumar Contractor, Shri Muktsar Sahib | 31-10-2013 | 31-10-2014 | 80% Completed | Sh. Yadwinder Singh Dhillion, Executive Engineer, Water supply and Sanitation Division No.1 Shri Muktsar Sahib | work in progress
WSS DIVN. MOGA
Prov. Water Supply Scheme at Bagha Purana Town, Distt. Moga
1 | Prov. & installing a Tubewell new 300x200mm i/d (each) with gravel packed upto 160 mtr. Depth. | 25.9 | 18.19 | 29.75% Below | 518/2010-11 | M/s Builder Home, Jagroan | 2011-02-25 | 31.03.2011 | 100% | Er. Balbir Singh, Executive Engineer, W/S & Sanitation Division, Moga (DAC Complex, Jehlam Chanab Building, Third Floor, Room No. 313,
2 | Construction of 4 Nos. RCC OHSR of 1.50 ltrs Capacity with FSL not to be less than 28.00 Mtr. And sill level not to be less than 23.50 mtr. at Bagha Purana Town | 150 | 65.9 | 56.06% Below | 511/2010-11 | M/s J.M.S Construction Co, Kale Ke Road, Bagha Purana | 2011-02-10 | 10.01.2012 | 100% | Er. Balbir Singh, Executive Engineer, W/S & Sanitation Division, Moga
3 | Installation of 05 Nos. Reverse Osmosis Water Treatment Plants at Bagha Purana Town, Distt. Moga | 92.5 | 50.41 | 45.50% Below | 528/2011-12 | M/s S.R. Paryavaran Pvt, Ltd, Panchkula | 2011-01-21 | 30.05.2011 | 100% | Er. Balbir Singh, Executive Engineer, W/S & Sanitation Division, Moga
4 | Construction of Rising Main at waer works Mahantan Wali Gali & M.C. Office Bagha Purana Town, Moga. | 3.99 | 3.98 | 0% | 628/2013-14 | Sh. Amit Bajaj, Contractor, VPO Mal Ke, Bagha Purana, Distt. Moga | 2013-01-04 | 2013-02-28 | 100% | Er. Balbir Singh, Executive Engineer, W/S & Sanitation Division, Moga | Work Completed but payment is still pending due to not submission of bill by contractor
5 | Prov. Water Supply Scheme at Bagha Purana Town, Distt. Moga. | 102.35 | 204.74 |  | 523/2011-12 | M/s Gautam Kalucha Contractor, Jalabad, Distt. Firozpur | 2011-04-25 | In Progress | 90% | Er. Balbir Singh, Executive Engineer, W/S & Sanitation Division, Moga | ork stopped by contractor due to not sufficient funds released by GLADA
374.74
Prov. Sewerage Scheme (North) (East) Zone & Sewerage Treatment Plant at Bagha Purana Town, Distt. Moga
1 | Providing, laying, Jointing, Testing, S.W/RCC Pipe sewer, excavation & refilling, construction of man hole chamber and all other works contingent there to at Bagha Purana Town, Distt. Moga. (For East Zone) (Funded by GLADA) | 630.46 | 711.15 | 12.79% Less |  | M/S Oberoi Construction Corporation, Deep Nagar-4, Kotkapura Road, Sh. Muktsar Sahib, | 2011-04-27 | In Progress | 80% | Er. Balbir Singh, Executive Engineer, W/S & Sanitation Division, Moga | Work stopped by contractor due to not sufficient funds released by GLADA
2 | Providing, laying, Jointing, Testing, S.W/RCC Pipe sewer, excavation & refilling, construction of man hole chamber and all other works contingent there to at Bagha Purana Town, Distt. Moga. (For West Zone) | 523.3 | 611.35 | 16.82% Less |  | M/S Kohli Builders, 12, Guru Angad Dev Nagar, Kotkapura Road, Sh. Muktsar Sahib. | 2011-04-27 | In Progress | 80% | Er. Balbir Singh, Executive Engineer, W/S & Sanitation Division, Moga | -do-
3 | Design Construction, erection, testing & Commissioning of (i) Main Pumping station (ii) Sewage Treatment plant based on moving bed biological reactor technology (Attached growth process) of 3.80 MLD capacity complete in all respects. Including construction of sullage carrier (iii) boundary wall (iv) staff quartersw, approach roads, MCC Panel room, DG set & all contingent electrical, mechanical, piping and instrumentation works including trial run & defect liability period of 90 days and operation & maintenance for 10 years thereafter at Nihal Singh Wala Road, Bahga Purana, Distt. Moga., PUNJAB | 472.50 & 120.00 for Land Acquisition | 582.07 | 23.18% Below |  | M/S Sourabh Constructions Pvt. Ltd. Opp. Mehta Dharmshala, Colony Road,, Mandi Dabwali, Distt. Sirsa (Haryana) | 2011-11-09 | In Progress | 90% | Er. Balbir Singh, Executive Engineer, W/S & Sanitation Division, Moga | -do-
Circle Bhatinda
Water Suply & Sanitation Divn. No. 1, Bathinda
1 | Providing Sewerage Scheme for Nar Singh Colony (Other Habitation of Village Doomwali) Block Sangat Distt. Bathinda (i) Package -I Civil Work | Rs. 376.86 lacs (Admn. Approval Amount) | 177.44 | 11.79% below | 163 of 2012 | Sh. Dawinder Kumar Contractor, Bathinda | 2012-07-20 | 2013-07-19 | Work Completed | Er. J.S. Chahal Executive Engineer, W/S & Sanitation Division No. 1, Bathinda | --
2 | (ii) Package -II Sewerage Treatment Plant |  | 125 | 13.35% below | 150 of 2011 | Hydrotech Paryavaran (India) Pvt. Ltd. Mohali | 2012-03-12 | 2014-01-31 | Work Commissioned |  | --
Water Suply & Sanitation Divn. No. 3, Bathinda
1 | Providing Laying and Rising Main Aug. of Head Water Works, Bhagu Road Bathinda. | Total Rs. 1391.44 Package III Rs. 418.06 (RCC OHSR,R/s Filteration, RCC OHSR) | 411.5 | 1.5% Below | -- | M/s Shree Balaji Construction Co., Bathinda | 2014-02-17 | Work in progress | RCC OHSR 95% completed and other work is in progress | Er. Jaswinder Singh EE W/S & Sanitation Division No 3, Bathinda
Water Suply & Sanitation Divn. No. 2, Mansa
1 | Aug. W/S Boha | Rs. 258.42 lacs (Admn. Approval Amount) | 253.74 | 2% above of SOR | 1091 of 03/14 | M/s Mankoo Builders, Bathinda | 04/03/14 | 03/03/15 | 20% work completed | Sh. Ravinder Singh Bansal, EE, W/S & Sanitation Division No. 2, Mansa
Circle Chandigarh
W/S & Sanitation Division No 1, SAS Nagar
1 | PROVIDING ESTATE PUBLIC HEALTH SERVICES I.E. ESTATE WATER SUPPLY, SEWERAGE & STORM WATER DRAINAGE, RAIN WATER HARVESTING, FIRE FIGHTING SYSTEM, VRV AIR CONDITIONING SYSTEM IN DISTT. ADMINISTRATIVE COMPLEX SECTOR 76, S.A.S. NAGAR | 545.96 | 535.81 | 1.86 | 1205 | M/S Deepak Builders, Near Lodhi Club,S.B.S. Nagar Ludhiana. | 2013-07-01 | 2014-12-01 | 58% | Er. J.S Dhami, W/S & Sanitation Division No. 1, Mohali | -
2 | PROVIDING, INSTALING, TESTING & COMMISSIONING VRV AIR-CONDITIONING PLANT IN ANAAJ BHAWAN (FOOD COMPLEX), PUN GRAIN BUILDING, SECTOR-39, CHANDIGARH AND ALL OTHER WORKS CONTINGENT THERETO. | 233.52 | 213.94 | 8.38 | 1344 | M/s Sky Line Air Conditioning Engineer (P) Ltd. E-76, LGF, Kalkaji, New Delhi | 2014-05-01 | 2014-10-01 | 86% | Er. J.S Dhami, W/S & Sanitation Division No. 1, Mohali | -
Circle Jalandhar
Division NO. 1 Jalandhar
1 | Prov. Sewerage Scheme & Sewerage Treatment Plant at the village Lohar Sukha Singh Block: Jalandhar East Dist.Jalandhar. | 196.57 | 209.18 | - | PRWSS-W-DIV13-1699-1/147 | M/s Obrai Const. Corporation, Shri Muktsar Sahib. | 31.10.2013 | Under Progress | 90% | Er. Paramjit Singh Executive Engineer Water Supply & Sanitation Division No.1 Jalandhar | -
2 | Prov.Sewerage Scheme & Sewerage Treatment Plant at the village Raipur Block: Jalandhar East Dist.Jalandhar. | 260.98 | 274.16 | - | PRWSS-W-DIV13-2307-1/77 | Sh Kuldip Singh Contractor, H.No 35, Sangam Enclave, Sector - 48A , Chandigarh | 30.07.2013 | Under Progress | 70% | Er. Paramjit Singh Executive Engineer Water Supply & Sanitation Division No.1 Jalandhar | -
Division NO. 2 Jalandhar
1 | Prov. Sewerage Scheme Kalra Block Adampur Distt. Jalandhar | 266.87 | 293.51 | 9.98% above | PRWSS-W-DIV14 -1691-1/127 | M/S Concept Chem – Werm India Ltd (JV) A-17, Second Floor, Tagore Market, Kirti Nagar, New Delhi – 110015 | 28.08.13 | 27.08.14 | 60% | Er. N.P Singh E.E W/S & Sanitation Division NO. 2 Jalandhar | --
2 | --do-- Padhiana Block Adampur | 305.62 | 336.13 | 9.98% above | DWSS-W-DIV14 -1695-1/134 | -do- | 29.08.13 | 28.08.14 | 60% | --do-- | --
3 | --do-- Rasulpur Kalan Block Nakodar Distt. Jalandhar | 203.55 | 242.48 | 15.71% above | PRWSS-W-DIV14 -1690-1/141 | -do- | 30.08.13 | 29.08.14 | 60% | --do-- | --
4 | --do-- Dhandowal Block Shahkot Distt. Jalandhar | 200.12 | 218.04 | 4.8% above | PRWSS-W-DIV14 -1689-1/155 | M/S Oberoi Construction Corp. 4, Deep Nagar, Kotkapura Road, Muktsar. | 31.10.13 | 30.10.14 | 90% | --do-- | --
Division Kapurthala
1 | Sewerage Scheme & Sewerage Treatment Plant Project Lakhan Kalan | 2.30 crore | 2.60 crore | 9.24% Above | -- | M/s. JM Enviro Technologies Pvt. Ltd New Delhi | 02.08.13 | Under process | 90% | Er. Sanjay Arora, W/s & Sanitation Division, Kapurthala
Circle Hoshiarpur
1 | Prov. Sewerage Scheme Bharoli Block Banga Distt. SBS Nagar | 258.73 | 264.38 | 2.18% above | PRWSS-W-DIV-21-1681-1 | M/S Khayti Heights Bhatinda | 15.07.2013 | 30.11.2014 | 90% | Er. Amarjit Singh, Executive Engineer, W/S & sanitation Division, SBS Nagar | Work in Progress
Circle Ludhiana
Water Supply & Sanitation Divn. No.2, Ludhiana
1 | Goindwal | 227.98 | Part A-219.32 & Part B- 13.82 lacs. | 3.8% below | 97 | M/s Gautam Kalucha | 5.07.2013 | 14.04.2014 | 97% | Eng. Rajesh Kumar Gupta, Executive Engineer, Water Supply & Sanitation Division No.2, Ludhiana.
2 | Akalgarh | 289.71 | Part A-282.58 & Part B- 22.34 lacs. | 2.48% below | 96 | Sh. Makhan Lal Jindal | 30.08.2013 | 29.08.2014 | 92%
3 | Ber Kalan | 220.93 | Part A-227.67 & Part B- 14.69 lacs. | 3.05% above | 93 | Sh. Makhan Lal Jindal | 24.05.2013 | 23.02.2014 | 85%
Circle Sangrur
W/S & Sanitation Div. Sangrur
1 | Small Bore Sewerage System House Connection & Sewerage treatment works at Village Aloarkh Block Bhawanigarh Distt. Sangrur | 205.12 Not Adm. Approval | 205.12 | 0 | 731 | Sh. Makhan Lal Jindal |  | 2012-09-12 | 100% | SDE No. 2, Sangrur
2 | Small Bore Sewerage System House Connection & Sewerage treatment works at Village Karyal Block Sunam Distt. Sangrur | 208.12 Not Adm. Approval | 208.12 | 0 | 734 | Sh. Makhan Lal Jindal |  | 27-08-2012 | 100% | Sh. Hemant Servia , SDE
W/S & Sanitation Div. Malerkotla
1 | Prov. Sewerage Scheme Jhaner Block Malerkotla-2 Distt. Sangrur | 199.02 | 220.44 | 10.76% Above | 155/2013-14 | Sh. Jai Bhushan Malik, Patiala | 2013-06-14 | 2014-03-13 | 100% Work Completed | Er. Kulwant Singh, Executive Engineer, W/S & Sanitation Division, Malerkotla
W/S & Sanitation Div. Barnala
1 | Kattu Sewerage Schme | 292.29 | 326.14 | 10.37% above | 21/2013-14 | M/S Jai Bhushan Malik | 24.7.2013 | 23.7.2014 | 100% | Sh. Rajinder Singh E.E W/S & Sanitation Division Barnala
Circle Patiala
Water Supply & Sanitation, Div. No. 2, Patiala
1 | Construction of Cattle Breeding Farm at Village Rauni, Block & District Patiala (Nabha Road, Patiala) | 409 | 255.74 | 0.86 % below | No. 1075 of 2014 | M/s ASC Builders Pvt, Ltd., Bathinda | 15.09.2014 | 14.09.2015 | Tubewell Installed, Work of OHSR in Progress | A.K. Bansal (Executive Engineer), WSS Div. No. 2, Patiala | Work in Progress, along with Building work
Water Supply & Sanitation Divn. Rajpura
1 | Installation of 37 Nos. Reverse Osmosis Plant on built own Operator transtfer (BOOT) Basis for 37 Nos. villages Block Rajpura, Ghanour and Sanour of Distt. Patiala (Cluster 8) | 472.4 | 453.9 | 3.92% Below | 4 of 2014 | M/s Doshion Velolia Water Solution (P) Ltd. Plot No. 24, Phase-II, GID Valva, Ahemdabad | 02.01.2014 | work in Progress | 10% work completed | Eng. Anil Kumar Executive Engineer Water Supply & Sanitation Division Rajpura.
Circle Ferozepur
EE WSS Divn. NO.2,Ferozepur
1 | Sewerage Scheme village Toot, Block Ghall Khurd, Distt. Ferozepur | 245.22 | 255.62 | 4.00% above | 76 | M/s Mittal Const. Co. Jaitu | 25.07.13 | 20.10.14 (Tentative) | 95% | Er. Sandip Singh J.E, O/o SDE WSS Sub-Div. Ghall Khurd | --
2 | Sewerage Scheme village Hardasa, Block Zira, Distt. Ferozepur | 195.16 | 212.16 | 8.00% above | 74 | Shish Pal Chander Cont. | 05.08.13 | 20.10.14 (Tentative) | 96% | Er. Gurmukh Singh J.E, O/o SDE WSS Sub-Div. No-1, Zira | --
Circle Amritsar
--------------------------- NIL ---------------------------
Circle Gurdaspur
-------------------------------------NIL-----------------------------
Chief Vigilance Officer
cum- Superintending Engineer
Water Supply & Sanitation Circle,
Patiala

## Proforma -II
Annexure-2
Sr. No. Of Bill | VR. No. Date | Account payable |  |  |  | Total (In Rs.) | Cheque amount (In Rs. | Details of disbursement and recoveries
|  | On A/C payment | Adv. Payment | Sceured advanced | Mobilisation advance |  |  | Adv. I/Tax | Cost of Material | Secured Adv. | Mob. Adv. | Deposit
Circle Faridkot
WSS DIVN. FARIDKOT
1 | Vr. No. 1 Dt. 02-03-2013 | 7579422 | - | - | - | 7579422 | 6518304 | 1061118 | - | - | - | -
2 | Vr. No. 12 Dt. 28-03-2013 | 7058125 | - | - | - | 7058125 | 6585987 | 472138 | - | - | - | -
3 | Vr. No. 13 Dt. 24-08-2013 | 5625440 | - | - | - | 5625440 | 4781625 | 843815 | - | - | - | -
4 | Vr. No. 22 Dt. 31-05-2014 | 3787013 | - | - | - | 3787013 | 3537183 | 249830 | - | - | - | -
5 | Vr. No. 25 Dt. 17-07-2014 | 1251779 | - | - | - | 1251779 | 1251779 | 0 | - | - | - | -
WSS DIVN. MALOUT
Water Supply
Danewal | Various vouchers No. bill No. | 9403000 | - | - | - | 9403000 | 8651000 | 752000 | - | - | - | -
Bharu | Various vouchers No. bill No. | 8286000 | - | - | - | 8286000 | 7623000 | 663000 | - | - | - | -
Shamkot | Various vouchers No. bill No. | 27169000 | - | - | - | 27169000 | 24995000 | 2174000 | - | - | - | -
Ghumiara | Various vouchers No. bill No. | 13848000 | - | - | - | 13848000 | 12740000 | 1108000 | - | - | - | -
Sewerage schemes
Middu Khera | Various Voucher No. | 32232000 | - | - | - | 32232000 | 29653000 | 2579000 | - | - | - | -
Beedowali | Various Voucher No. | 30550000 | - | - | - | 30550000 | 28106000 | 2444000 | - | - | - | -
Ghumiar Khera | Various Voucher No. | 18761000 | - | - | - | 18761000 | 17260000 | 1501000 | - | - | - | -
Daula | Various Voucher No. | 21770000 | - | - | - | 21770000 | 20028000 | 1742000 | - | - | - | -
WSS DIVN. NO.1 MUKTSAR
CC First & Running Bill | 41, 25-3-14 | 3353250 | 0 | 0 | 0 | 3353250 | 2917326 | 435924 | 0 | 0 | 0 | 0
2nd Running Bill | 57, 26-03-14 | 4437000 | 0 | 0 | 0 | 4437000 | 3860190 | 576810 | 0 | 0 | 0 | 0
3rd Running bill | - | 5500000 | 0 | 0 | 0 | 5500000 | 5060000 | 4040000 | 0 | 0 | 0 | 0
Ist Running Bill | 48, 28-12-13 | 4999050 | 0 | 0 | 0 | 4999050 | 4349172 | 649878 | 0 | 0 | 0 | 0
2nd Running Bill | 1, 01-02-14 | 7087450 | 0 | 0 | 0 | 7087450 | 6166080 | 921370 | 0 | 0 | 0 | 0
3rd Running bill | 7, 23-05-14 | 4159820 | 0 | 0 | 0 | 4159820 | 3619044 | 540776 | 0 | 0 | 0 | 0
Secured Advanced | 8, 23-05-14 | 0 | 0 | 5655200 | 0 | 5655200 | 4920024 | 735176 | 0 | 0 | 0 | 0
4th Running Bill | 6, 23-05-14 | 14738484 | 0 | 0 | 0 | 14738484 | 7902457 | 1180827 | 0 | 5655200 | 0 | 0
5th Running Bill | 4, 07-07-14 | 6675814 | 0 | 0 | 0 | 6675814 | 6141749 | 534065 | 0 | 0 | 0 | 0
6th Running bill | - | 7467302 | 0 | 0 | 0 | 7467302 | 6869918 | 597384 | 0 | 0 | 0 | 0
7th Running Bill | - | 2994145 | 0 | 0 | 0 | 2994145 | 2754614 | 239531 | 0 | 0 | 0 | 0
WSS DIVN. MOGA
Instalation of T/wells (M/S Builder, Jagraon)
CC 1st & Final Bill | BP 86 of 3/11 | T/ Well | - | - | - | - | 831385 | 9341 | - | - | - | 46707
CC 1st & Final Bill | Div. 4 of 4/11 | T/ Well | - | - | - | - | 871370 | 9270 | - | - | - | -
Total | [6 empty] | 1702755 | 18611 |  |  |  | 46707
Cosntruction of OHSRs (M/s J.M.S. Construction Co, Kale Ke Road, Bagha Purana)
Hand Recept. | Div. 56 of 4/6/11 | Construction of 4 Nos. RCC OHSR of 1.50 ltrs Capacity with FSL not to be less than 28.00 Mtr. And sill level not to be less than 23.50 mtr. at Bagha Purana Town | - | - | - | - | 2758250 | 59317 | - | - | - | -
Hand Recept. | Div. 43 of 1/12 |  | - | - | - | - | 1072652 | 23068 | - | - | - | -
1st & Final Bill | Div. 51 of 8/11 |  | - | - | - | - | 1739971 | 39545 | - | - | - | 98862
2nd & Final Bill | Div. 2 of 8/12 |  | - | - | - | - | 494310 | 9886 | - | - | - | -
Total |  |  | 0 |  |  | 0 | 6065183 | 131816 |  |  |  | 98862
Installation of R.O Plants (M/s S.R. Paryavaran Pvt. Ltd)
| 31 of 6/11 | Installation of 05 Nos. Reverse Osmosis Water Treatment Plants at Bagha Purana Town, Distt.Moga | - | - | - | - | 843897 | 63519 | - | - | - | -
| 32 of 6/11 |  | - | - | - | - | 843897 | 63519 | - | - | - | -
| 33 of 6/11 |  | - | - | - | - | 843897 | 63519 | - | - | - | -
| 34 of 6/11 |  | - | - | - | - | 843897 | 63519 | - | - | - | -
| 35 of 6/11 |  | - | - | - | - | 843897 | 63519 | - | - | - | -
[7 empty] | 4219485 | 317595
Total | [6 empty] | 4219485 | 317595
M/S Kholi Builder
| 6 of 5/11 | Providing laying, jointing, Testing, S.W/RCC Pipe Sewe,r Excavation & refilling, construction of man hole chamber and all other works contingent there to at Bagha Purana Town,Distt.Moga.(for East Zone) | - | 11283650 | - | 11283650 | 10493795 | 789855 | - | - | - | -
| 25 of 8/11 |  | - | - | - | 11928468 | 4000000 | 834993 | - | 1000000 | - | -
| 10 of 1/12 |  | - | - | - | 1155044 | 10374191 | 780853 | - | 1000000 | - | -
| 5 of 9/12 |  | - | - | - | - | 3892067 | 357891 | - | 4000000 | - | -
| 4 of 3/13 |  | - | - | - | 1638089 | 1425138 | 212951 | - | 5283650 | - | -
Total |  |  |  | 11283650 |  | 26005251 | 30185191 | 2976543 |  | 11283650
M/S Oberoi Constuction
CC 1st | SDE BP 5 of 5/11 | Providing laying, jointing, Testing, S.W/RCC Pipe Sewe,r Excavation & refilling, construction of man hole chamber and all other works contingent there to at Bagha Purana Town,Distt.Moga.(for East Zone) (Funded by GLADA) | - | 13820800 | - | 13820800 | 12853344 | 967456 | - | - | - | -
cc 2nd & Final | Div. 44 of 7/11 |  | - | - | - | - | 1265500 | 1006687 | - | - | - | 719063
cc 3rd R/Bill | 1 of 10/11 |  | - | - | - | - | 11429327 | 909152 | - | 2000000 | - | -
cc 4th R/Bill | Div.80 of 1/12 |  | - | - | - | - | 6161918 | 566612 | - | 1000000 | - | 354133
CC 5th & R/Bill | Div. 5 of 5/12 |  | - | - | - | - | 4643112 | 426452 | - | 6000000 | - | 266845
CC 6th & R/Bill | 1 of 10/12 |  | - | - | - | - | 11161645 | 1026360 | - | 2000000 | - | 641475
CC 6th & R/Bill | - |  | - | - | - | - | 3498465 | 321698 | - | 1700000 | - | 201061
Total |  |  | 0 | 13820800 |  | 13820800 | 51013311 | 5224417 |  | 12700000 |  | 2182577
M/S Gautam Kalucha Cont.
| 7 of 3/11 | Prov. Water Supply Scheme at Bagha Purana Town,Distt. Moga. |  | 10747750 | - | 10747750 | 10102886 | 644864 | PVC Pipe | - | - | -
| 47 of 27/4 |  | - | - | - | - | 3059148 | 243341 | - | 5000000 | - | -
| 9 of 1/12 |  | - | - | - | - | 3564010 | 227490 | - | 2000000 | - | -
Total |  |  |  | 10747750 |  | 10747750 | 16726044 | 1115695 |  | 7000000
M/S Sourabh Constusctions Pvt.Ltd
CC 1st R/ Bill | Div. 24 of 3/12 | Design Construction,erection testing & Commissioning of (i) Main Pumping station (ii) Sewage Treatment plant based on moving bed biological reactor technology ( Atteched growth process) of 3.80 MLD capacity comlete in all respects. | - | - | - | 4179398 | 3845046 | 334352
CC 2nd R/Bill | Div. 7 of 7/3/14 |  | - | - | - | 13783884 | 11645170 | 1240550 |  |  |  | 898164
CC 3rd R/Bill | Div. 9 of 8/3/14 V.No.8 of 7/4/14 |  | - | - | - | 5515367 | 4743216 | 496383 |  |  |  | 275768
CC 4th & R/Bill | 12 of 10/4/14 |  | - | - | - | 4978537 | 4281542 | 448068 |  |  |  | 248927
CC 5th & R/Bill | Div. 25 of 4/14 |  | - | - | - | 6662334 | 5729607 | 599610 | - | - | - | 333117
CC 6th & R/Bill | Div. 5 of 9/6/14 |  | - | - | - | 7981766 | 6864319 | 718359 | - | - | - | 399088
Total | [5 empty] | 43101286 | 37108900 | 3837322 |  |  |  | 2155064
Circle Bhatinda
Water Supply & Sanitation Divn. No. 1, Bathinda
Package No. -1 Sh. Davinder Kumar Contractor, Bathinda
1 | 21/27-08-2012 | -- | -- | 1485188 | -- | 1485188 | 406964 | 14852 | -- | -- | -- | 74260
2 |  | 3047683 | -- | -- | -- | 3047683 | 2681961 | 30477 | -- | -- | -- | 152384
3 |  | 2457370 | -- | -- | -- | 2457370 | 2150198 | 24574 | -- | -- | -- | 122869
4 |  | 3241575 | -- | -- | -- | 3241575 | 2836376 | 32416 |  |  |  | 162080
5 |  | 2307502 | -- | -- | -- | 2307502 | 2019064 | 23075 |  |  |  | 115375
6 |  | 1743405 | -- | -- | -- | 1743405 | 1525480 | 17434 |  |  |  | 87170
7 |  | 2084740 | -- | -- | -- | 2084740 | 1793471 | 20847 |  |  |  | 104237
8 |  | 1089033 | -- | -- | -- | 1089033 | 1001911 | 10890 |  |  |  | --
Package No. -2 Hydrotech Paryavaran (India) Pvt. Ltd. Mohali
1 | 21/27-08-2012 | 1592500 | -- | -- | -- | 1592500 | 1055100 | 31850 | -- | -- | -- | 30000
2 |  | 1265000 | -- | -- | -- | 1265000 | 895925 | 25300 | -- | -- | -- | 142875
3 |  | 1147500 | -- | -- | -- | 1147500 | 810825 | 22950 | -- | -- | -- | 57375
4 |  | 283700 | -- | -- | -- | 283700 | 2128094 | 56758 | -- | -- | -- | 141895
5 |  | 1931100 | -- | -- | -- | 1931100 | 1660746 | 38622 | -- | -- | -- | 96500
Water Supply & Sanitation Divn. No. 3, Bathinda
CC1 | 9/21-02-2014 | 9000000 | -- | -- | -- | -- | 9000000 | 920000 | -- | -- | -- | --
CC2 | 12/13-05-2014 | 500000 | -- | -- | -- | -- | 500000 | 1317562 | -- | -- | -- | --
CC3 | 17/26-06-2014 | 1607124 | -- | -- | -- | -- | 1607124 | 261626 | -- | -- | -- | --
CC4 | 8/28-07-2014 | 3680744 | -- | -- | -- | -- | 3680744 | 599190 | -- | -- | -- | --
CC5 | 1/25-08-2014 | 7311720 | -- | -- | -- | -- | 7311720 | 1190280 | -- | -- | -- | --
Water Supply & Sanitation Divn. No. 2, Mansa
1 | 9-21/4/14 | 1030000 | -- | -- | -- | 1030000 | 885000 | 92700 | -- | -- | -- | 51500
2 | 1-14/7/14 | 1776150 | -- | -- | -- | 1776150 | 1524488 | 159854 | -- | -- | -- | 88808
3 | 1-10/9/14 | 1514670 | -- | -- | -- | 1514670 | 1302615 | 136321 | -- | -- | -- | 75734
4 | 5-23/9/14 | 1248000 | -- | -- | -- | 1248000 | 1050000 | 112320 | -- | -- | -- | 85680
Circle Chandigarh
W/S & Sanitation Division No 1, SAS Nagar
Account Maintained by B& R Department
1 | 2/ 14-9-14 | 18912825/- | - | - | - | 18912825/- | 16265029/- | 378256/- | - | - | - | 945641/-
Circle Jalandhar
DIV No 1 Jalandhar
Lohar Sukha Singh |  | 4017450 | - | - | - | 4017450 | 3414833 | 80349 |  | - | - | 522268
1 | 1 dt. 03.02.2014 | - | - | 3888983 | - | 3888983 | 3888983 | - | - | - | - | -
2 | 13 dt. 23.05.2014 | 1711017 | - | - | - | 1711017 | 1454365 | 34220 | - | - | - | 222432
3 | 17 dt. 23.05.2014 | 997000 | - | - | - | 997000 | 422981 | 76537 | - | 1690950 | - | 497482
4 | 6 dt. 7.07.2014 | 1139187 | - | - | - | 1139187 | 1139187 | - | - | - | - | -
5 | 2 dt. 17.09.2014
Raipur |  | - | - | 2191239 | - | 2191239 | 2191239 | - | - | - | - | -
1 | 16 dt. 06.11.2013 | - | - | 627465 | - | 627465 | 627465 | - | - | - | - | -
2 | 7 dt. 18.01.2014 | 3437015 | - | - | - | 3437015 | 2894477 | 38753 | - | 432248 | - | 503785
3 | 13 dt 18.01.2014 | 1786111 | - | - | - | 1786111 | 1479023 | 21935 | - | 407364 | - | 285153
4 | 10 dt. 24.06.2014 | 926879 | - | - | - | 926879 | 717593 | 14906 | - | 281871 | - | 194380
5 | 6 dt. 24.06.2014
DIV No 2 Jalandhar
|  | 0 |  | 2160000 | 0 | 2160000 | 2160000 | 0 | 0 | 0 | 0 | 0
148 | 24 dt. 18-1-14 | 0 |  | 1269000 | 0 | 1269000 | 1269000 | 0 | 0 | 0 | 0 | 0
27 | 17 dt. 24-6-14 | 4154000 |  | 0 | 0 | 4154000 | 1971000 | 374000 | 0 | 1560000 | 0 | 249000
48 | 11 dt. 28-8-14 | 4154000 | 13139 | 3429000 | 0 | 7583000 | 5400000 | 374000 | 0 | 1560000 | 0 | 249000
| Total |  |  | Sewerage Project Padhiana
|  | 0 |  | 2041000 | 0 | 2041000 | 2041000 | 0 | 0 | 0 | 0 | 0
149 | 20 dt. 18-1-14 | 0 |  | 849000 | 0 | 849000 | 849000 | 0 | 0 | 0 | 0 | 0
26 | 11 dt. 24-6-14 | 2679000 |  | 0 | 0 | 2679000 | 1971000 | 425000 | 0 | 0 | 0 | 283000
36 | 18 dt. 24-6-14 | 3402000 |  | 0 | 0 | 3402000 | 2680000 | 306000 | 0 | 212000 | 0 | 204000
47 | 2 dt. 28-8-14 | 6081000 | 86296 | 2890000 | 0 | 8971000 | 7541000 | 731000 | 0 | 212000 | 0 | 487000
| Total |  |  | Sewerage Project Rasulpur Kalan
166 | 6 dt. 12-3-14 | 3544000 |  | 0 | 0 | 3544000 | 3083000 | 284000 | 0 | 0 | 0 | 177000
28 | 14 dt. 24-6-14 | 149000 |  | 0 | 0 | 179000 | 917000 | 108000 | 0 | 0 | 0 | 54000
49 | 3 dt. 28-8-14 | 0 |  | 12.81 | 0 | 1281000 | 1281000 | 0 | 0 | 0 | 0 | 0
| Total | 3693000 | 13139 | 12.81 | 0 | 5004000 | 5281000 | 392000 | 0 | 0 | 0 | 231000
Sewerage Project Dhandowal
160 | 2 dt. 3-2-14 | 3264000 |  | 0 | 0 | 3264000 | 2774000 | 294000 | 0 | 0 | 0 | 196000
172 | 15 dt. 12-3-14 | 1738000 |  | 0 | 0 | 1738000 | 1470000 | 157000 | 0 | 0 | 0 | 104000
10 | 4 dt. 23-5-14 | 0 |  | 15.01 | 0 | 1501000 | 1276000 | 135000 | 0 | 0 | 0 | 90000
25 | 13 dt. 24-6-14 | 0 |  | 20 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0
33 | 15 dt. 24-6-14 | 0 |  | 22.74 | 0 | 2274000 | 2274000 | 0 | 0 | 0 | 0 | 0
55 | 4 dt. 28-8-14 | 4470000 |  | 0 | 0 | 4470000 | 2134000 | 402000 | 0 | 16.66 | 0 | 268000
| Total | 9472000 | 53361 | 57.75 | 0 | 15247000 | 11928000 | 988000 | 0 | 16.66 | 0 | 658000
DIV KAPURTHALA
|  | -- | -- | Secured advanced | -- | 537918 | 537918 | 10979 | -- | -- | -- | --
233 | No. 4 dated 06.11.13 | On A/C Payment | -- | -- | -- | 2116134 | 2116134 | 49212 | -- | -- | -- | 123031
303 | No. 6 dated 28.12.13 | On A/C Payment | -- | -- | -- | 1595703 | 1595703 | 32565 | -- | -- | -- | --
345 | No. 12 dated 29.01.2014 | On A/C Payment | -- | -- | -- | 1242313 | 1242313 | 30371 | -- | -- | -- | 72312
360 | No. 6 dated 12.03.14 | On A/C Payment | -- | -- | -- | 503795 | 503795 | -- | -- | -- | -- | --
361 | No. 13 dated 12.03.14 | On A/C Payment | -- | -- | -- | 1718000 | 1718000 | 42000 | -- | -- | -- | 100000
1001 | No. 5 dated 03.06.14 | On A/C Payment | -- | -- | -- | 4111987 | 4111987 | 106812 | -- | -- | -- | 361459
1012 | No. 8 dated 29.09.14 | On A/C Payment | -- | -- | -- | 4062911 | 4062911 | 99326 | -- | -- | -- | 236491
Circle Hoshiarpur
Secured Advance | 3/14-9-2013 | -- | -- | 1474032 | -- | 1474032 | 1356110 | 14740 | -- | -- | - | --
Ist Running Bill | 18/13-12-2013 | 1906513 | -- | 0 | -- | 1906513 | 1554261 | 18138 | -- | 92760 | -- | 114391
2nd Secured Advance | 5/18-1-2014 | -- | -- | 3108752 | -- | 3108752 | 2860051 | 31088 | -- | 0 | --
2nd Running Bill | 7/13-3-2014 | 3718321 | -- | -- | -- | 3718321 | 3138196 |  | -- | 992673 | -- | 282660
3rd Running Bill | 13/24-6-2014 | 3552000 | -- | -- | -- | 3552000 | 2959317 | 35520 | -- | 1497291 | -- | 308523
4th Running Bill | 152/26-8-2014 | 3890824 | -- | -- | -- | 3890824 | 3290862 | 38908 | -- | 920798 | -- | 288697
5 th Running Bill |  | 2119386 | -- | -- | -- | 2119386 | 1779567 | 21194 | -- | 718416 | -- | 170268
6 th Running Bill |  | 754756 | -- | -- | -- | 754756 | 627439 | 7548 | -- | 360846 | -- | 66936
Circle Ludhiana
Water Supply & Sanitation Divn. No.2, Ludhiana
Goindwal
232 | - | - | - | 2297673 | - | 2297673 | - | - | - | - | - | -
240 | - | - | - | 1224000 | - | 1224000 | - | - | - | - | - | -
281 | - | 1361420 | - | - | - | 1361420 | - | - | - | 1234798 | - | -
310 | - | 4000000 | - | - | - | 4000000 | - | - | - | - | - | -
501 | - | 1885533 | - | - | - | 1885533 | - | - | - | 1138166 | - | -
502 | - | 1584999 | - | - | - | 1584999 | - | - | - | - | - | -
513 | - | 2183070 | - | - | - | 2183070 | - | - | - | 1300000 | - | -
534 | - | 2862362 | - | - | - | 2862362 | - | - | - | 1000000 | - | -
Akalgarh
188 | - | - | - | 2672000 | - | 2672000 | - | - | - | - | - | -
192 | - | - | - | 3505586 | - | 3505586 | - | - | - | - | - | -
278 | - | 4474961 | - | - | - | 4474961 | - | - | - | 2612938 | - | -
512 | - | 1300000 | - | - | - | 1300000 | - | - | - | - | - | -
514 | - | 3691000 | - | - | - | 3691000 | - | - | - | 1483500 | - | -
537 | - | 4187052 | - | - | - | 4187052 | - | - | - | 1000000 | - | -
Ber Kalan
170 | - | - | - | 1790338 | - | 1790338 | - | - | - | - | - | -
175 | - | - | - | 3793662 | - | 3793662 | - | - | - | - | - | -
257 | - | - | - | 4119904 | - | 4119904 | - | - | - | - | - | -
266 | - | 4711040 | - | - | - | 4711040 | - | - | - | 3001952 | - | -
535 | - | 2820418 | - | - | - | 2820418 | - | - | - | 1500000 | - | -
Circle Sangrur
W/S & Sanitaion Division, Sangrur
2006-06-01 | 3/19.6.06 | 38570 | 0 | 0 | 0 | 38570 | 37667 | 903 | 0 | 0 | 0 | 0
2006-07-01
2006-08-01
2006-09-01 | 5/7.9.06 | 3043229 | 0 | 0 | 0 | 3043229 | 2758991 | 132077 | 0 | 0 | 0 | 152161
2006-10-01
2006-11-01
2006-12-01
2007-01-01
2007-02-01
2007-03-01
2007-04-01
2007-05-01
2007-06-01
2007-07-01
2007-08-01
2007-09-01
2007-10-01 | 3/15.7.07 | 1238972 | 0 | 0 | 0 | 1238972 | 1050000 | 54353 | 0 | 0 | 0 | 134619
2007-11-01
2007-12-01
2008-01-01
2008-02-01
2008-03-01
2008-04-01
2008-05-01
2008-06-01
2008-07-01
2008-08-01 | 4/21.8.08 | 993236 | 0 | 0 | 0 | 993236 | 830940 | 62972 | 0 | 0 | 0 | 99324
2008-09-01
2008-10-01
2008-11-01
2008-12-01
2009-01-01
2009-02-01
2009-03-01
2009-04-01
2009-05-01
2009-06-01
2009-07-01
2009-08-01
2009-09-01
2009-10-01
2009-11-01
2009-12-01
2010-01-01
2010-02-01
2010-03-01
2010-04-01
2010-05-01
2010-06-01
2010-07-01
2010-08-01
2010-09-01
2010-10-01
2010-11-01
2010-12-01
2011-01-01
2011-02-01
2011-03-01
2011-04-01
2011-05-01
2011-06-01
2011-07-01
2011-08-01
2011-09-01
2011-10-01
2011-11-01
2011-12-01
2012-01-01
2012-02-01
2012-03-01
2012-04-01 | 2/23.4.12 | 4818712 | 0 | 0 | 0 | 4818712 | 2900000 | 385498 | 0 | 0 | 0 | 1533214
2012-05-01
2012-06-01 | 5/22.6.12 | 2587541 | 0 | 0 | 0 | 2587541 | 2251161 | 207003 | 0 | 0 | 0 | 129377
2012-07-01
2012-08-01
2012-09-01
2012-10-01
2012-11-01 | 3/23.11.12 | 4859230 | 0 | 0 | 0 | 4859230 | 4227529 | 388739 | 0 | 0 | 0 | 242962
2012-12-01
2013-01-01
2013-02-01
2013-03-01
2013-04-01
2013-05-01
2013-06-01
2013-07-01
2013-08-01
2013-09-01
2013-10-01
2013-11-01
2013-12-01
2014-01-01
2014-02-01
2014-03-01 | 3/14.3.14 | 819929 | 0 | 0 | 0 | 819929 | 660135 | 118798 | 0 | 0 | 0 | 40996
W/S & Sanitaion Division, Malerkotla
2006-05-01 | 68 No. 2 Sangrur | 56000 | 0 | 0 | 0 | 56000
2006-06-01 | 5 | 53100 | 0 | 0 | 0 | 53100 | 51857 | 1243 | 0 | 0 | 0 | 0
2006-07-01
2006-08-01 | 2/8.8.06 | 2402879 | 0 | 0 | 0 | 2402879 | 2178451 | 104285 | 0 | 0 | 0 | 120143
2006-09-01 | 1 Div. | 44596 | 0 | 0 | 0 | 44596 |  |  | 0 | 0 | 0
2006-10-01
2006-11-01
2006-12-01
2007-01-01
2007-02-01
2007-03-01
2007-08-01 | 1/4.8.07 | 2518257 | 0 | 0 | 0 | 2518257 | 2283053 | 109292 | 0 | 0 | 0 | 125912
2007-05-01
2007-06-01
2007-07-01
2007-08-01
2007-09-01
2007-10-01
2007-11-01
2007-12-01
2008-01-01
2008-02-01
2008-03-01
2008-04-01
2008-05-01
2008-06-01
2008-07-01
2008-08-01
2008-09-01 | 2/2.9.08 | 689556 | 0 | 0 | 0 | 689556 | 576882 | 43718 | 0 | 0 | 0 | 68956
2008-10-01
2008-11-01
2008-12-01
2009-01-01
2009-02-01
2009-03-01
2009-04-01
2009-05-01
2009-06-01
2009-07-01
2009-08-01
2009-09-01
2009-10-01
2009-11-01
2009-12-01
2010-01-01
2010-02-01
2010-03-01
2010-04-01
2010-05-01
2010-06-01
2010-07-01
2010-08-01
2010-09-01
2010-10-01
2010-11-01
2010-12-01
2011-01-01
2011-02-01
2011-03-01
2011-04-01
2011-05-01
2011-06-01
2011-07-01
2011-08-01
2011-09-01
2011-10-01
2011-11-01
2011-12-01
2012-01-01
2012-02-01
2012-03-01
2012-04-01
2012-05-01
2012-06-01 | 4/22.6.14 | 6504409 | 0 | 0 | 0 | 6504409 | 5160921 | 457259 | 0 | 0 | 0 | 886229
2012-07-01
2012-08-01
2012-09-01 | 3/14.9.12 | 6533146 | 0 | 0 | 0 | 6533146 | 4462170 | 457319 | 0 | 0 | 0 | 1613657
2012-10-01
2012-11-01 | 6/23.11.12 | 2122586 | 0 | 0 | 0 | 2122586 | 1846648 | 169808 | 0 | 0 | 0 | 106130
2012-11-01 | 1/6.11.12 | 602802 | 0 | 0 | 0 | 602802 | 602802 | 0 | 0 | 0 | 0 | 0
2012-12-01
2013-01-01
2013-02-01
2013-03-01
2013-04-01
2013-05-01
2013-06-01
2013-07-01
2013-08-01
2013-09-01
2013-10-01
2013-11-01
2013-12-01
2014-01-01
2014-02-01
2014-03-01 | 5/14.3.14 | 435206 | 0 | 0 | 0 | 435206 | 339458 | 30467 | 0 | 0 | 0 | 65281
2014-04-01
2014-05-01
2014-06-01
2014-07-01
2014-08-01 | 2/13.8.14 | 599000 | 0 | 0 | 0 | 599000 | 521130 | 47920 | 0 | 0 | 0 | 29950
2013-08-01 | 1/26.08.13 | 7546342 | 0 | 0 | 0 | 7546342 | 6565318 | 603707 | 0 | 0 | 0 | 377317
2013-09-01 | 2/11.09.13 | 3268415 | 0 | 0 | 0 | 3268415 | 2965662 | 261473 | 0 | 0 | 0 | 41280
2013-10-01 | 3/23.10.13 | 5485195 | 0 | 0 | 0 | 5485195 | 4772120 | 438816 | 0 | 0 | 0 | 274259
2014-01-01 | 6/24.01.14 | 1801642 | 0 | 0 | 0 | 1801642 | 1567432 | 144130 | 0 | 0 | 0 | 90080
2014-09-01 | 14/05.09.14 | 1520414 | 0 | 0 | 0 | 1520414 | 1307556 | 121633 | 0 | 0 | 0 | 91225
W/S & Sanitaion Division, Barnala
120/12.9.13 | 3.10.13 | -- | -- | 9656159 | -- | 9656159 | 8980227 | 96562 | 9656159 | -- | -- | --
117/ 6.9.13 | 24.9.13 | -- | -- | -- | -- | 4314244 | 3710250 | 43142 | -- | -- | -- | 258855
137/29.9.13 | 19.11.13 | -- | -- | -- | -- | 1470000 | 1264200 | 14700 | -- | -- | -- | 88200
159/27.10.13 | 9.12.13 | -- | -- | -- | -- | 2475444 | 2128882 | 24754 | -- | -- | -- | 148527
172/ 13.11.13 | 7.12.13 | -- | -- | -- | -- | 1623316 | 1396052 | 16233 | -- | -- | -- | 97399
138/13.8.14 | 30.8.14 | -- | -- | -- | -- | 2890819 | 2486105 | 28908 | -- | -- | -- | 173449
149/19.8.14 | 30.8.14 | -- | -- | -- | -- | 427243 | 371702 | 4272 | -- | -- | -- | 25635
Circle Patiala
Water Supply & Sanitation Divn. Rajpura
122 | 5 dt. 1.7.14 | 842328 | -- | -- | -- | 842328 | 766518 | -- | -- | -- | -- | --
123 | 2 dt. 1.7.14 | 842328 | -- | -- | -- | 842328 | 766518 | -- | -- | -- | -- | --
124 | 3 dt. 1.7.14 | 842328 | -- | -- | -- | 842328 | 766518 | -- | -- | -- | -- | --
125 | 1 dt. 1.7.14 | 949596 | -- | -- | -- | 949596 | 864132 | -- | -- | -- | -- | --
126 | 4 dt. 1.7.14 | 949596 | -- | -- | -- | 949596 | 864132 | -- | -- | -- | -- | --
144 | -- | 533480 | -- | -- | -- | 533480 | 448016 | -- | -- | -- | -- | --
145 | -- | 416116 | -- | -- | -- | 416116 | 416116 | -- | -- | -- | -- | --
Circle Ferozepur
EE WSS Divn. NO.2,Ferozepur
Sewerage Scheme Hardasa
1 | 1 dt. 07.10.13 |  |  |  |  | 1609076 | 1391850 | 16091 | 0 | 0 | 0 | 96545
2 | 1 dt. 01.11.13 |  |  |  |  | 3223145 | 1401762 | 32231 | 0 | 0 | 0 | 1563533
3 | 2 dt. 05.11.13 |  |  |  |  | 1370145 | 1370145 |  | 0 | 0 | 0 | 0
4 | 3 dt. 05.11.13 |  |  |  |  | 3716685 | 3196349 | 37167 | 0 | 0 | 0 | 223001
5 | 1 dt. 25.12.13 |  |  |  |  | 3280733 | 2788624 | 32807 | 0 | 0 | 0 | 196844
6 | 2 dt. 23.06.14 |  | Mail Today |  |  | 6964 | 6964 | 0 | 0 | 0 | 0 | 0
7 | 3 dt. 23.06.14 |  | Daily Suraj |  |  | 3250 | 3250 | 0 | 0 | 0 | 0 | 0
8 | 4 dt. 23.06.14 |  | Janta Express |  |  | 3108 | 3108 | 0 | 0 | 0 | 0 | 0
9 | 5 dt. 23.06.14 |  | Jagran Parkash |  |  | 11092 | 11092 | 0 | 0 | 0 | 0 | 0
10 | 6 dt. 23.06.14 |  | Daily Ajit |  |  | 16475 | 16475 | 0 | 0 | 0 | 0 | 0
11 | 7 dt. 23.06.14 |  |  |  |  | 5245583 | 2727618 | 52456 | 0 | 0 | 0 | 2098318
12 | 14, dt. 17.09.14 |  |  |  |  | 1783583 | 1783583 | 0 | 0 | 0 | 0 | 0
13 | 1 dt. 23.06.14 | PSPCL |  |  |  | 7880 | 7880 | 0 | 0 | 0 | 0 | 0
| Total |  |  |  |  | 20277719 | 14708700 | 170752 | 0 | 0 | 0 | 4178241
Sewerage Scheme Toot
1 | 1 dt. 06.11.13 |  |  |  |  | 4357449 | 3790982 | 43574 | 0 | 0 | 0 | 217872
2 | 1 dt. 07.12.13 |  |  |  |  | 5200962 | 4524836 | 52010 | 0 | 0 | 0 | 260048
3 | 1 dt. 22.01.14 |  |  |  |  | 4568694 | 3929076 | 45687 | 0 | 0 | 0 | 228435
4 | 1 dt. 23.06.14 |  | Punjab Kesri |  |  | 29141 | 29141 | 0 | 0 | 0 | 0 | 0
5 | 2 dt. 23.06.14 |  | Punjab Kesri |  |  | 17549 | 17549 | 0 | 0 | 0 | 0 | 0
6 | 3 dt. 23.06.14 |  | Jag Bani |  |  | 4178 | 4178 | 0 | 0 | 0 | 0 | 0
7 | 4 dt. 23.06.14 |  | Punjab Kesri |  |  | 6938 | 6938 | 0 | 0 | 0 | 0 | 0
8 | 5 dt. 23.06.14 |  | Janch Chowkat |  |  | 2518 | 2518 | 0 | 0 | 0 | 0 | 0
9 | 6 dt. 23.06.14 |  | Janch Chowkat |  |  | 599 | 599 | 0 | 0 | 0 | 0 | 0
10 | 7 dt. 23.06.14 |  | Janta Express |  |  | 3684 | 3684 | 0 | 0 | 0 | 0 | 0
11 | 8 dt. 23.06.14 |  | Mail Today |  |  | 8605 | 8605 | 0 | 0 | 0 | 0 | 0
12 | 9 dt. 23.06.14 |  | Mail Today |  |  | 2049 | 2049 | 0 | 0 | 0 | 0 | 0
13 | 11 dt. 23.06.14 |  |  |  |  | 3696239 | 3215729 | 36962 | 0 | 0 | 0 | 184812
14 | 01 dt. 01.07.14 |  |  |  |  | 1057500 | 920025 | 10575 | 0 | 0 | 0 | 52875
Sewerage Scheme Toot
15 | 10 dt. 23.06.14 | PSPCL |  |  |  | 7880 | 7880 | 0 | 0 | 0 | 0 | 0
| Total |  |  |  |  | 18963985 | 16463789 | 188808 | 0 | 0 | 0 | 944042
Circle Amritsar
--------------------------- NIL ---------------------------
Circle Gurdaspur
-------------------------------------NIL-----------------------------
Chief Vigilance Officer
cum- Superintending Engineer
Water Supply & Sanitation Circle,
Patiala